## PROJECT_PHASES_WITH_EXPENSES
SUMMARY PROJECT ROLLOUT PHASES WITH EXPENSES
PHASES | DESCRIPTION | TIMELINES | INR | USD | REMARKS
PHASE I | Extending the Platform, Integrating ERPNext and Bank. | 6 Months
EXPENSE 1 | Onetime Platform Extension |  | 4680900 | 56396.3855
EXPENSE 2 | Onetime Integrations |  | 1427800 | 17202.4096
EXPENSE 3 | Onetime Legal |  | 67142 | 808.9398
|  | Sub Total | 6175842 | 74407.7349
PHASE II | Load Testing and Field Trials in Ernakulam District | 1 Month
EXPENSE 4 | Annually Recurring Platforms Maintaining Cost under COGS Head |  | 10095156.8 | 121628.3952
EXPENSE 5 | Manpower Recruitment at 14 Districts to keep them Standby |  | 826000 | 9951.8072
EXPENSE 6 | Deploy Manpower for the Field Trials in Ernakulam District |  | 150000 | 1807.2289
|  | Sub Total | 11071156.8 | 133387.4313
PHASE III | Pilot in Ernakulam District | 2 Months
EXPENSE 7 | Deploy Manpower for the Pilot in Ernakulam District |  | 750000 | 9036.1446
PHASE IV | Go Live in Ernakulam District | 3 Months |  |  | Read Comment
EXPENSE 8 | Deploy Manpower for Go Live in Ernakulam District |  | 1125000 | 13554.2169
PHASE V | Go Live across the entire State of Kerala | 6 Months |  |  | Read Comment
EXPENSE 9 | Deploy Manpower for Go Live across the entire State of Kerala |  | 18000000 | 216867.4699
Total |  |  | 37121998.8 | 447252.9976
PHASE VI | Extended Year Sponsorship | 12 Months
EXPENSE 10 | SG&A and COGS for One Year |  | 46095156.8 | 555363.3349
Grand Total |  |  | 83217155.6 | 1002616.3325
Note on F15: "All platforms will go live after undergoing prior trials, resolving any technical glitches, and training the entire team, engaging personnel in a phased manner, and providing salaries and honorariums for both back office and field personnel."
Note on F17: Timelines are based on the approximate minimum time required to enroll Vendor Partners, Delivery Partners, and acquire customers in their respective geographical territories.

## ONETIME_PLATFORM_EXTENSION_COGS
ONE TIME EXPENSES UNDER COGS HEAD – EXTENDING THE PLATFORMS
S.NO. | DESCRIPTION OF SERVICE | PROPOSED SERVICE PROVIDER | QTY | TENTATIVE COST | GST @18% | TOTAL IN INR | TOTAL IN USD
1 | Apnafood Platform on IOS | Vasavi College of Engineering | 1 | 200000 | 36000 | 236000 | 2843.3735
2 | Apnafood Platform User Documentation | Vasavi College of Engineering | 1 | 20000 | 3600 | 23600 | 284.3373
3 | Apnafood Platform Developer Documentation | Vasavi College of Engineering | 1 | 25000 | 4500 | 29500 | 355.4217
4 | Apnafood Platform Wiki | Vasavi College of Engineering | 1 | 10000 | 1800 | 11800 | 142.1687
5 | Apnafood Platform Training | Vasavi College of Engineering | 1 | 25000 | 4500 | 29500 | 355.4217
1 | Apnaride Platform SRS Preparation | Vasavi College of Engineering | 1 | 15000 | 2700 | 17700 | 213.253
2 | Apnaride Platform on Android and Web | Vasavi College of Engineering | 1 | 400000 | 72000 | 472000 | 5686.747
3 | Apnaride Platform on IOS | Vasavi College of Engineering | 1 | 100000 | 18000 | 118000 | 1421.6867
4 | Apnaride Platform User Documentation | Vasavi College of Engineering | 1 | 20000 | 3600 | 23600 | 284.3373
5 | Apnaride Platform Developer Documentation | Vasavi College of Engineering | 1 | 25000 | 4500 | 29500 | 355.4217
6 | Apnaride Platform Wiki | Vasavi College of Engineering | 1 | 10000 | 1800 | 11800 | 142.1687
7 | Apnaride Platform Training | Vasavi College of Engineering | 1 | 25000 | 4500 | 29500 | 355.4217
1 | Apnaservices Platform SRS Preparation | Vasavi College of Engineering | 1 | 15000 | 2700 | 17700 | 213.253
2 | Apnaservices Platform on Android and Web | Vasavi College of Engineering | 1 | 400000 | 72000 | 472000 | 5686.747
3 | Apnaservices Platform on IOS | Vasavi College of Engineering | 1 | 100000 | 18000 | 118000 | 1421.6867
4 | Apnaservices Platform User Documentation | Vasavi College of Engineering | 1 | 20000 | 3600 | 23600 | 284.3373
5 | Apnaservices Platform Developer Documentation | Vasavi College of Engineering | 1 | 25000 | 4500 | 29500 | 355.4217
6 | Apnaservices Platform Wiki | Vasavi College of Engineering | 1 | 10000 | 1800 | 11800 | 142.1687
7 | Apnaservices Platform Training | Vasavi College of Engineering | 1 | 25000 | 4500 | 29500 | 355.4217
1 | Apnacart B2C Platform SRS Preparation | Vasavi College of Engineering | 1 | 15000 | 2700 | 17700 | 213.253
2 | Apnacart B2C Platform on Android and Web | Vasavi College of Engineering | 1 | 400000 | 72000 | 472000 | 5686.747
3 | Apnacart B2C Platform on IOS | Vasavi College of Engineering | 1 | 100000 | 18000 | 118000 | 1421.6867
4 | Apnacart B2C Platform User Documentation | Vasavi College of Engineering | 1 | 20000 | 3600 | 23600 | 284.3373
5 | Apnacart B2C Platform Developer Documentation | Vasavi College of Engineering | 1 | 25000 | 4500 | 29500 | 355.4217
6 | Apnacart B2C Platform Wiki | Vasavi College of Engineering | 1 | 10000 | 1800 | 11800 | 142.1687
7 | Apnacart B2C Platform Training | Vasavi College of Engineering | 1 | 25000 | 4500 | 29500 | 355.4217
1 | Apnacart B2B Platform SRS Preparation | Vasavi College of Engineering | 1 | 15000 | 2700 | 17700 | 213.253
2 | Apnacart B2B Platform on Android and Web | Vasavi College of Engineering | 1 | 400000 | 72000 | 472000 | 5686.747
3 | Apnacart B2B Platform on IOS | Vasavi College of Engineering | 1 | 100000 | 18000 | 118000 | 1421.6867
4 | Apnacart B2B Platform User Documentation | Vasavi College of Engineering | 1 | 20000 | 3600 | 23600 | 284.3373
5 | Apnacart B2B Platform Developer Documentation | Vasavi College of Engineering | 1 | 25000 | 4500 | 29500 | 355.4217
6 | Apnacart B2B Platform Wiki | Vasavi College of Engineering | 1 | 10000 | 1800 | 11800 | 142.1687
7 | Apnacart B2B Platform Training | Vasavi College of Engineering | 1 | 25000 | 4500 | 29500 | 355.4217
1 | Apnacredit Platform SRS Preparation | Vasavi College of Engineering | 1 | 15000 | 2700 | 17700 | 213.253
2 | Apnacredit Platform on Android and Web | Vasavi College of Engineering | 1 | 400000 | 72000 | 472000 | 5686.747
3 | Apnacredit Platform on IOS | Vasavi College of Engineering | 1 | 100000 | 18000 | 118000 | 1421.6867
4 | Apnacredit Platform User Documentation | Vasavi College of Engineering | 1 | 20000 | 3600 | 23600 | 284.3373
5 | Apnacredit Platform Developer Documentation | Vasavi College of Engineering | 1 | 25000 | 4500 | 29500 | 355.4217
6 | Apnacredit Platform Wiki | Vasavi College of Engineering | 1 | 10000 | 1800 | 11800 | 142.1687
7 | Apnacredit Platform Training | Vasavi College of Engineering | 1 | 25000 | 4500 | 29500 | 355.4217
1 | Implementing Online and Offline Effort Capturing System | Vasavi College of Engineering | 1 | 500000 | 90000 | 590000 | 7108.4337
2 | Low Capacity Server Hosting (Holding Containers) for One Year | Contabo | 1 | 250000 | NA | 250000 | 3012.0482
TOTAL |  |  |  | 3255000 | 585900 | 4680900 | 56396.3855

## ONETIME_INTEGRATIONS_COGS
ONE TIME EXPENSES UNDER COGS HEAD – ERP IMPLEMENTATION AND INTEGRATIONS
S.NO. | DESCRIPTION OF SERVICE | QTY | TENTATIVE COST | GST | TOTAL IN INR | TOTAL IN USD
1 | Integration of ERP with DBS Bank | 1 | 200000 | 36000 | 236000 | 2843.3735
2 | Integration of ERP with Platforms | 1 | 100000 | 18000 | 118000 | 1421.6867
3 | Implementing ERP Accounting with Chart of Accounts | 1 | 50000 | 9000 | 59000 | 710.8434
4 | Implementing ERP Projects | 1 | 25000 | 4500 | 29500 | 355.4217
5 | Integration of ERPNext TimeSheets with OpenStreetMap | 1 | 25000 | 4500 | 29500 | 355.4217
6 | Implementing osTicket Ticketing for Helpdesk | 1 | 300000 | 54000 | 354000 | 4265.0602
7 | Integration of Hosted Telephony with ERP | 1 | 50000 | 9000 | 59000 | 710.8434
8 | Implementing Tile Server for OpenStreetMap | 1 | 50000 | 9000 | 59000 | 710.8434
9 | Implementing ERP Survey System using Quality Feedback | 1 | 50000 | 9000 | 59000 | 710.8434
10 | Implementing ERPNext Voting System | 1 | 50000 | 9000 | 59000 | 710.8434
11 | Implementing Metabase Dash Board | 1 | 100000 | 18000 | 118000 | 1421.6867
12 | One Time Online Training on ERPNext Accounting | 1 | 30000 | 5400 | 35400 | 426.506
13 | One Time Online Training on ERPNext Projects | 1 | 30000 | 5400 | 35400 | 426.506
14 | One Time Online Training on ERPNext TimeSheets | 1 | 30000 | 5400 | 35400 | 426.506
15 | One Time Online Training on ERPNext Ticketing | 1 | 30000 | 5400 | 35400 | 426.506
16 | One Time Online Training on ERPNext Hosted Telephony | 1 | 30000 | 5400 | 35400 | 426.506
17 | One Time Online Training on ERPNext Survey System | 1 | 30000 | 5400 | 35400 | 426.506
18 | One Time Online Training on ERPNext Voting System | 1 | 30000 | 5400 | 35400 | 426.506
TOTAL |  |  | 1210000 | 217800 | 1427800 | 17202.4096

## ONETIME_LEGAL_COGS
ONE TIME LEGAL & STATUTORY EXPENSES
S.NO. | ACCOUNTS HEAD | DESCRIPTION OF SERVICE | PROPOSED SERVICE PROVIDER | QTY | UNIT PRICE | GST @18% | TOTAL IN INR
| LEGAL | Privacy Policy | Liberators | 1 | 5000 | 900 | 5900 | 71.0843
1 |  | Delivery Partner Agreement | “ | 1 | 5000 | 900 | 5900 | 71.0843
2 |  | Vendor Partner Agreement | “ | 1 | 5000 | 900 | 5900 | 71.0843
3 |  | Terms and Conditions | “ | 1 | 5900 | 1062 | 6962 | 83.8795
4 |  | GST for Kerala | “ | 1 | 1000 | 180 | 1180 | 14.2169
5 |  | FSSAI Licence for Kerala | “ | 1 | 15000 | 2700 | 17700 | 213.253
6 |  | State Public Limited Incorporation | “ | 1 | 15000 | 2700 | 17700 | 213.253
7 |  | Agreement Execution | “ | 1 | 5000 | 900 | 5900 | 71.0843
TOTAL | [6 empty] | 67142 | 808.9398

## HR_RECRUITMENT
MANPOWER RECRUITMENT ENGAGING HUMAN RESOURCE CONSULTING FIRM
ITEM | INR | GST@18% | TOTAL
MANPOWER RECRUITMENT AT 14 DISTRICTS | 700000 | 126000 | 826000
TOTAL |  |  | 826000

## IDENTITY_PROVISIONS
ONE TIME EXPENSES SUMMARY
ITEM | INR | QTY | TOTAL | REMARKS
T-SHIRTS | 0 |  | 0 | Planned for Later
CAPS | 0 |  | 0 | Planned for Later
ID CARDS | 0 |  | 0 | Planned for Later
CARRY BAGS | 0 |  | 0 | Planned for Later
TOTAL |  |  | 0

## RECURRING_COGS
YEARLY EXPENSES UNDER COGS HEAD
S.No. | DESCRIPTION OF SERVICE | MONTHLY | YEARLY | GST@18% | TOTAL | PROPOSED SERVICES WEBSITES
DATA CENTER HOSTING
1 | Platforms Private Cloud Hosting @Datacenter | 150000 | 1800000 | NA | 1800000 | Contabo
2 | Private Cloud Infrastructure Management | 80000 | 960000 | NA | 960000 | Canonical
3 | ERPNext Hosting @Datacenter | 11800 | 141600 | NA | 141600 | ERPNext
4 | Mithranjali Web Server Hosting @Datacenter | 6000 | 72000 | NA | 72000 | Mithranjali
5 | Nextcloud with Email & Collaboration Services Hosting @Datacenter | 14160 | 169920 | NA | 169920 | NextCloud
6 | NEWS Letter Server Hosting @Datacenter | 6000 | 72000 | NA | 72000 | phpList
7 | Zabbix for Infrastructure Monitoring Hosting @Datacenter | 6000 | 72000 | NA | 72000 | Zabbix
8 | Tile Server for OpenStreetMap | 14160 | 169920 | NA | 169920 | Open Street Map
9 | Metabase Dashboard Server | 14160 | 169920 | NA | 169920 | Metabase
TECHNICAL SUPPORT
1 | Platforms Maintenance | 100000 | 1200000 | 216000 | 1416000
2 | ERPNext Support | 100000 | 1200000 | 216000 | 1416000 | ERPNext
3 | Metabase Dashboard and Analytics | 120000 | 1440000 | NA | 1440000 | Metabase
SEO
1 | Monster Insights | 0 | 17500 | NA | 17500 | MonsterInsights
2 | Yoast SEO | 0 | 19000 | NA | 19000 | YoastSEO
3 | Diib Traffic Plus SEO Checker | 665 | 7980 | NA | 7980 | DiiB
4 | Web, SEO, wiki, NEWS Letter, Social Content Writing | 6000 | 72000 | 12960 | 84960 | Credible Content Writing
OTHER SERVICES
1 | Ticketing System for Helpdesk | 20000 | 240000 | NA | 240000 | osTicket
2 | Content Delivery Services | 13500 | 162000 | NA | 162000 | Fastly
3 | Graylog for External Log @Greylog | 13500 | 162000 | NA | 162000 | Greylog
4 | Hosted Telephony | 7080 | 84960 | 15292.8 | 100252.8 | Servetel
5 | SMS Services for OTP | 6900 | 82800 | 14904 | 97704 | Textlocal
6 | Continuous Audit Services of Nodes | 7700 | 92400 | NA | 92400 | Rudder
SOCIAL MEDIA DIGITAL OUTREACH
1 | Social Media Digital Outreach | 50000 | 600000 | 108000 | 708000
MAPPING AND MAINTENANCE
1 | OpenStreetMap Training by OSM India Foundation’s Kerala Volunteers and for Regular Updates | 42000 | 504000 | NIL | 504000 | Open Street Map
TOTAL | Diib Traffic Plus SEO Checker |  | 9512000 |  | 10095156.8

## HR_FIELD_TRIALS_ERNAKULAM
HUMAN RESOURCES EXPENSES SUMMARY FOR FIELD TRIALS IN ERNAKULAM DISTRICT
MANPOWER | NOS | MONTHLY | MONTHLY TOTAL
Vendor Development Sales Coordinators on Field | 2 | 15000 | 30000
Enrolment and System Manning Coordinators | 2 | 15000 | 30000
Services Delivery and Helpdesk Coordinators | 2 | 15000 | 30000
Other Back Office Coordinators | 2 | 15000 | 30000
Coordinators on Field | 2 | 15000 | 30000
TOTAL | 10 | 75000 | 150000

## HR_PILOT_ERNAKULAM
HUMAN RESOURCES EXPENSES SUMMARY FOR PILOT IN ERNAKULAM DISTRICT
MANPOWER | NOS | MONTHLY | MONTHLY TOTAL | 2 MONTHLY TOTAL
Vendor Development Sales Coordinators on Field | 7 | 15000 | 105000 | 210000
Enrolment and System Manning Coordinators | 7 | 15000 | 105000 | 210000
Services Delivery and Helpdesk Coordinators | 7 | 15000 | 105000 | 210000
Other Back Office Coordinators | 2 | 15000 | 30000 | 60000
Coordinators on Field | 2 | 15000 | 30000 | 60000
TOTAL | 25 | 75000 | 375000 | 750000

## HR_GO_LIVE_ERNAKULAM
HUMAN RESOURCES EXPENSES SUMMARY FOR GO LIVE IN ERNAKULAM DISTRICT
MANPOWER | NOS | MONTHLY | MONTHLY TOTAL | 3 MONTHLY TOTAL
Vendor Development Sales Coordinators on Field | 7 | 15000 | 105000 | 315000
Enrolment and System Manning Coordinators | 7 | 15000 | 105000 | 315000
Services Delivery and Helpdesk Coordinators | 7 | 15000 | 105000 | 315000
Other Back Office Coordinators | 2 | 15000 | 30000 | 90000
Coordinators on Field | 2 | 15000 | 30000 | 90000
TOTAL | 25 | 75000 | 375000 | 1125000

## HR_GO_LIVE_KERALA
HUMAN RESOURCES EXPENSES SUMMARY FOR GO LIVE IN KERALA STATE
MANPOWER | NOS | MONTHLY | MONTHLY TOTAL | 6 MONTHLY TOTAL
Vendor Development Sales Coordinators on Field | 156 | 15000 | 2340000 | 14040000
Enrolment and System Manning Coordinators | 17 | 15000 | 255000 | 1530000
Services Delivery and Helpdesk Coordinators | 17 | 15000 | 255000 | 1530000
Other Back Office Coordinators | 5 | 15000 | 75000 | 450000
State Level Agency Coordinators on Field | 5 | 15000 | 75000 | 450000
TOTAL | 200 | 75000 | 3000000 | 18000000

## EXTENDED_YEAR_SPONSORSHIP
EXTENDED YEAR EXPENSES
MANPOWER | NOS | MONTHLY | MONTHLY TOTAL | 12 MONTHLY TOTAL
Vendor Development Sales Coordinators on Field | 156 | 15000 | 2340000 | 28080000
Enrolment and System Manning Coordinators | 17 | 15000 | 255000 | 3060000
Services Delivery and Helpdesk Coordinators | 17 | 15000 | 255000 | 3060000
Other Back Office Coordinators | 5 | 15000 | 75000 | 900000
State Level Agency Coordinators on Field | 5 | 15000 | 75000 | 900000
Annually Recurring COGS for Platforms | NA |  |  | 10095156.8
TOTAL | 200 | 75000 | 3000000 | 46095156.8